## WBS
1. WBS & Development Effort
No | Summary | Detail | Effort (Man-hour) | Note
For Clients: UD Invoice App
Base Project
0 | Init base project | Create base project, folder structure, source control | 8
Main features
1 | Implement Keycloak toggle functionality | Keycloak Enabled: Configure request authentication and integrate login API. Keycloak Disabled: Configure internal authentication using user data from the database. | 8
2 | Complete Keycloak integration and user synchronization. | Implement APIs for login, logout and refresh token. Implement AuditorAware for tracking changes in the system. Synchronize users between Keycloak and the internal database. | 8
3 | Develop basic user management APIs | Start basic user management APIs: Create user. Soft delete user. | 8
4 | Develop advanced user management APIs | Complete basic user management APIs: Lock/Unlock user. Develop advanced user management APIs: Reset password. View user list (support search and pagination). | 8
5 | Implement RBAC functionality | Develop RBAC functionality: CRUD for permissions and roles. Apply soft delete functionality across the system. | 8
6 | Finalize RBAC and refine user roles | Continue RBAC functionality: Assign permissions to roles and roles to users. Create default roles: User Manager. System Administrator. | 8
7 | Add logging functionality & configure Swagger | Configure Swagger for automatic API documentation. Log requests, responses, and exceptions. Exclude sensitive information from logs. | 8
8 | Prepare project details and testing | Write project details in README.md. Perform system-wide testing and validate all functionalities. Prepare progress reports and finalize documentation. | 8
|  | SUM (hour) | 72

## Master Plan
|  |  | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2
STT | Nội dung triển khai | Thời gian | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23
0 | Init base project | 26/11-26/11 | bar: 2024-11-26
1 | Implement Keycloak toggle functionality | 27/11-27/11 | bar: 2024-11-27
2 | Complete Keycloak integration and user synchronization. | 28/11-28/11 | bar: 2024-11-28
3 | Develop basic user management APIs | 29/11-29/11 | bar: 2024-11-29
4 | Develop advanced user management APIs | 02/12-02/12 | bar: 2024-12-02
5 | Implement RBAC functionality | 03/12-03/12 | bar: 2024-12-03
6 | Finalize RBAC and refine user roles | 04/12-04/12 | bar: 2024-12-04
7 | Add logging functionality & configure Swagger | 05/12-05/12 | bar: 2024-12-05
8 | Prepare project details and testing | 05/12-05/12 | bar: 2024-12-05